## SCHEDULE
Sprint Schedules (HPS MEC Project) (w.e.f. 17 Aug 2015)
S.No | Description | Day Scheduled | Time | Max. Duration | Attendees | Outputs | Remarks
1 | Daily Sprint Meeting (DSM) | All Days of Week | 9:30 | 15 Minutes | All Team Members | Previous Day's acheivements / Synchronize activities, Plan for next 24 Hours | First Day of Week - DSM is only to listen if anyone has concerns or changes to estimated values
2 | Sprint Planning (II) | Last sprint Day of week | 11:00 | 1 Hour | All Team Members | Preparation of Product Backlog Items, Division into Sub Tasks and Definition of Done for each Sub Task
3 | Sprint Review Meeting | Last Day of Week | 15:00 | 1 Hour | All Team Members | Demonstrate to Client what has been done during the week and get their feedback.
4 | Sprint Retrospective Meeting | Last Day of Week | 16:00 | 1 Hour | All Team Members | Review what has been done during the week. Identify any Weakness that needs to be attended, Identify best practices that can be followed going forward. | Retrospective on the currently completed SPRINT.

## DETERMINE SPRINT HOURS HPS
DASHBOARD FOR SPRINT AVAILABLE TIME
Week Details
Week No | 1
Week Start Date | 17/Aug/2015
Week End Date | #NAME?
No. of Working Days in the Week | 10
Working Hours Per Day | 0.33333
SPRINT TIME ALLOCATION
Total Working Hours in the Week | 480:00
Resource Non-availability Hours | #ERROR!
Time Allocation for Critical Support | 0:00
Planned Hours for Sprint Formalities | 0:00
Working Hours available for Sprint Development | #ERROR!
Allocation for Sprint Activities
Name of Resource | Total Available Time | Planned Leaves | Planned Permissions | Planned allocation for Critical Support | Identified for Sprint Planning (II)? | Resource Non-Availability Hours | Availability for Sprint | Time in Sprint Formalities | Time available for Dev. | Time for Allocated Tasks | Time Left with Associate | Remarks
| HH:MM | Days | HH:MM | HH:MM | Yes/No | HH:MM | HH:MM | HH:MM | HH:MM | HH:MM | HH:MM
Veeramani | 80:00 | 0 | 0:00 | 0 | Yes | #ERROR! | #ERROR! | Err:508 | #ERROR! | 0 | #ERROR!
Anandkumar | 80:00 | 0 | 0:00 | 0 | Yes | #ERROR! | #ERROR! | Err:508 | #ERROR! | 0 | #ERROR!
Johnson | 80:00 | 0 | 0:00 | 0 | Yes | #ERROR! | #ERROR! | Err:508 | #ERROR! | 0 | #ERROR!
Ashok | 80:00 | 0 | 0:00 | 0 | Yes | #ERROR! | #ERROR! | Err:508 | #ERROR! | 0 | #ERROR!
Vishwanathan | 80:00 | 0 | 0:00 | 0 | Yes | #ERROR! | #ERROR! | Err:508 | #ERROR! | 0 | #ERROR!
Chenna Readdy | 80:00 | 0 | 0:00 | 0 | Yes | #ERROR! | #ERROR! | Err:508 | #ERROR! | 0 | #ERROR!
Venkatesh P
Total | 480:00 | 0 | 0:00 | 0:00 |  | #ERROR! | #ERROR! | 0:00 | #ERROR! | 0:00 | #ERROR!
Time for Sprint Formalities | Time
Sprint Planning (I) | 1:00
Sprint Review Meeting | 1:00
Sprint Restrospective Meeting | 1:00
Other Mandatory Activity 1 | 0:00
Other Mandatory Activity 2 | 0:00
Total Common Activities | 03:00
Daily Sprint Meeting (DSM) | 0:15
Sprint Planning (II) | 1:00
Yes
No

## Sprint1 Task Plan
MEC 1095 – IRS Dev Plan – Sprint 1 (17 -08 -2015 – 28 -08 -2015)
|  |  | Coding |  |  |  |  | Code Rework | [5 empty] | Code Review | [5 empty] | Internal Testing
Module | Task | Sub Task | Name | Start Date | End Date | Planned Hrs | Hours | Name | Start Date | End Date | Planned Hrs | Hours | Comments | Name | Start Date | End Date | Planned Hrs | Hours | Comments | Name | Start Date | End Date | Planned Hrs | Hours | Comments
HTML5 UI | complete HTML5 UI design based on the given Mock up
|  | 1.DashBoard (Home) | Ashok | 17-08-2015 | 17-08-2015
|  | 2.Covered Individuals page(Parent Screen) | Ashok | 17-08-2015 | 17-08-2015
|  | 3.Create batch Page | Vishwanathan | 17-08-2015 | 17-08-2015
|  | 3.1. Popup 1: Print 1095-B form popup from view created Batch Page. | Vishwanathan | 17-08-2015 | 17-08-2015
|  | 3.2.Popup : Excluded From Batch popup from Create batch Page. | Vishwanathan | 17-08-2015 | 17-08-2015
|  | 4.View Created Batch Page. | Ashok | 17-08-2015 | 17-08-2015
|  | 4.1. Popup 1: Print 1095-B form popup from view created Batch Page. | Ashok | 17-08-2015 | 17-08-2015
|  | 4.2. Popup 2: Cancel Batch popup from view Created Batch Page. | Ashok | 17-08-2015 | 17-08-2015
|  | 4.3. Popup 3: View Batch log popup from View Created Batch Page. | Ashok | 18-08-2015 | 18-08-2015
|  | 4.4.Popup 4: View Batch Member log popup from View Created Batch Page. | Ashok | 18-08-2015 | 18-08-2015
|  | 5. Generate/View IRS file page. | Chenna Reddy | 17-08-2015 | 17-08-2015
|  | 5.1. Popup 1: Generate IRS file popup from Generate/View IRS file page. | Chenna Reddy | 17-08-2015 | 17-08-2015
|  | 5.2.Popup 2: IRS File Status Update popup Generate/View IRS file page. | Chenna Reddy | 17-08-2015 | 17-08-2015
Project Structure/Components/Updates from Client/Sprint Plan | Implementation of Components | Print Component | Veeramani | 17-08-2015 | 18-08-2015
|  | Export Component(Custom Format) | Veeramani | 19-08-2015 | 20-08-2015
|  | Exception Handling | Veeramani | 21-08-2015 | 24-08-2015
|  | Sprint 2 Planning | Veeramani | 25-08-2015 | 25-08-2015
Document | complete set of documents before start of developing.
| Flow and Design Document. | 1.Login | Chenna Reddy | 18-08-2015 | 18-08-2015
|  | 2.Data Sync | Chenna Reddy | 19-08-2015 | 19-08-2015
|  | 3.Covered Individual (Parent Page) | Chenna Reddy | 18-08-2015 | 18-08-2015
|  | 4.Create Batch | Chenna Reddy | 18-08-2015 | 18-08-2015
|  | 5.View Batch | Vishwanathan | 18-08-2015 | 18-08-2015
|  | 6.Generate IRS File | Vishwanathan | 18-08-2015 | 18-08-2015
|  | 7.e Filing | Vishwanathan | 19-08-2015 | 19-08-2015
|  | 8.IRS Response | Vishwanathan | 20-08-2015 | 20-08-2015
|  | 9.Corrected Batch | Vishwanathan | 20-08-2015 | 20-08-2015
Technical Design Document with master test criteria.
|  | 1.Login | AnandKumar | 17-08-2015 | 17-08-2015
|  | 2.Data Sync | AnandKumar | 17-08-2015 | 17-08-2015
|  | 3.Covered Individual (Parent Page) | AnandKumar | 17-08-2015 | 17-08-2015
|  | 4.Create Batch | AnandKumar | 18-08-2015 | 18-08-2015
|  | 5.View Batch | Chenna Reddy | 20-08-2015 | 20-08-2015
|  | 6.Generate IRS File | Chenna Reddy | 20-08-2015 | 20-08-2015
|  | 7.e Filing | AnandKumar | 19-08-2015 | 19-08-2015
|  | 8.IRS Response | AnandKumar | 20-08-2015 | 20-08-2015
|  | 9.Corrected Batch | AnandKumar | 20-08-2015 | 20-08-2015
UAT Document.
|  | 1.Login | Johnson | 17-08-2015 | 17-08-2015
|  | 2.Data Sync | Johnson | 17-08-2015 | 17-08-2015
|  | 3.Covered Individual (Parent Page) | Johnson | 17-08-2015 | 17-08-2015
|  | 4.Create Batch | Johnson | 18-08-2015 | 18-08-2015
|  | 5.View Batch | Johnson | 18-08-2015 | 18-08-2015
|  | 6.Generate IRS File | Johnson | 18-08-2015 | 18-08-2015
|  | 7.e Filing | Johnson | 19-08-2015 | 19-08-2015
|  | 8.IRS Response | Johnson | 19-08-2015 | 19-08-2015
|  | 9.Corrected Batch | Johnson | 19-08-2015 | 19-08-2015
Data Base | MEC Database creation (1095 B/ 1095 C) (Master Tables)
|  | 1.Participant List | Ashok | 19-08-2015 | 19-08-2015
|  | 2.DependentList | Ashok | 19-08-2015 | 19-08-2015
|  | 3.Employer Master | Ashok | 19-08-2015 | 19-08-2015
|  | 4.Issuer Master | Ashok | 19-08-2015 | 19-08-2015
|  | 5.Coverage Ledger | Ashok | 19-08-2015 | 19-08-2015
|  | 6.WorkFlow | Ashok | 19-08-2015 | 19-08-2015
MEC Database creation (1095 B/ 1095 C) (Transaction Tables)
|  | 1.Batch List | Ashok | 19-08-2015 | 19-08-2015
|  | 2.Batch Member Details | Ashok | 19-08-2015 | 19-08-2015
|  | 3.Exception Report | Ashok | 19-08-2015 | 19-08-2015
|  | 4.Address Exception | Ashok | 19-08-2015 | 19-08-2015
|  | 5.Exclude Batch | Ashok | 19-08-2015 | 19-08-2015
MEC Database creation (1095 B/ 1095 C) (Authentication Tables)
|  | 1.User | Ashok | 19-08-2015 | 19-08-2015
|  | 2.User Role | Ashok | 19-08-2015 | 19-08-2015
MEC Database creation (1095 B/ 1095 C) (Log Tables)
|  | 1.Process Log | Ashok | 19-08-2015 | 19-08-2015
|  | 2.Audit Log/History Table | Ashok | 19-08-2015 | 19-08-2015
Data Sync | Data sync configuration between TA and MEC
|  | 1.Create interface between TA and MED | Johnson | 20-08-2015 | 20-08-2015
|  | 2.User authentication | Johnson | 20-08-2015 | 20-08-2015
|  | 3.Read veiw from TA | Johnson | 21-08-2015 | 21-08-2015
|  | 4.Load data from from TA to MEC | Johnson | 24-08-2015 | 24-08-2015
|  | 5.Audit data (Data integrity) | Johnson | 24-08-2015 | 24-08-2015
|  | 6.Update back to Novus | Johnson | 24-08-2015 | 24-08-2015
Batch Action(Dev) | Create Batch | 1.Load memeber and dependent details for a selected year | Ashok | 20-08-2015 | 20-08-2015
|  | 2.Include/Exclude Action | Ashok | 20-08-2015 | 20-08-2015
|  | 3.Reason for Include/Exclude Action | Ashok | 21-08-2015 | 21-08-2015
|  | 4.Print preview | AnandKumar | 21-08-2015 | 25-08-2015
|  | 5. Validation action mandatory fields | Ashok | 21-08-2015 | 21-08-2015
|  | 6. Validation on address based on client requirement | Vishwanathan | 21-08-2015 | 25-08-2015
|  | 7. Ignore the member exception action | Ashok | 24-08-2015 | 24-08-2015
|  | 8. Generate Batch | Ashok | 25-08-2015 | 25-08-2015
|  | 9.Update Address back to TA event in Grid | Chenna Reddy | 21-08-2015 | 25-08-2015
|  | 5.Print Pdf/Export customized format | Veeramani | 24-08-2015 | 28-08-2015
Covered Individual Page(Parent Page)
|  | 1.Load memeber and dependent details for default year | Johnson | 25-08-2015 | 25-08-2015
Internal Testing | Test case document | 1.Master Test Criteria | Venkatesh P | 17-08-2015 | 18-08-2015
|  | 2.Internal Test case Doc | Venkatesh P | 19-08-2015 | 25-08-2015
| Testing | All Modules | Venkatesh P | 26-08-2015 | 28-08-2015
Bug Fixing
| Rework | All Modules | All Team Members | 26-08-2015 | 28-08-2015

## Sprint Info
| Hours | Start Date | End Date | Total Days | Total Developers
Sprint 1 | 80 | 17 – 08 – 2015 | 28 – 08 -2015 | 10 | 8
Sprint 2 | 80 | 01-09-2015 | 14-09-2015 | 10 | 8
Sprint 3 | 80 | 16-09-2015 | 30-09-2015 | 10 | 8
Sprint 4 | 80 | 5-09-2015 | 16-10-2015 | 10 | 8
Sprint 5 | 80 | 19-10-2015 | 30-10-2015 | 10 | 8
Sprint 6 | 80 | 2-11-2015 | 16-11-2015 | 10 | 8
Sprint 7 | 80 | 18-11-2015 | 1-12-2015 | 10 | 8
Total | 560 |  |  | 70 | 56(Source)